{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Master Task List"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Master Task List","index":0,"n_rows":208,"n_cols":11,"rows_kept":208,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,null,null,"MUSR 2010"]
[null,"Task #",null,"Task","AO","Date","Start","End","Follows","Resources","Comments / Status"]
[1,0,0,"Administration"]
[1,0,1,"Finalize Schedule"]
[1,0,2,"Finalize Hotel"]
[1,1,0,"Web Page"]
[1,1,1,"Register Domain"]
[1,1,2,"Complete Logo"]
[1,1,3,"Assemble Splash Page"]
[1,1,4,"Assemble Info Pages"]
[1,2,0,"Coordinate for Insurance"]
[1,2,1,"Forms to PCA Region"]
[1,2,2,"Forms to National"]
[1,2,3,"Get Insurance Certificate"]
[1,2,4,"Validate Costs"]
[1,2,5,"Coordinate Payment"]
[1,3,0,"Coordinate for PCA Subsidy"]
[1,3,1,"Forms to HOD Region"]
[1,3,2,"Forms to District"]
[1,3,3,"Forms to National"]
[1,3,4,"Flyer to National"]
[1,3,5,"Confirm Subsidy Payment to Region"]
[1,4,0,"Announce on Forums"]
[1,4,1,"914 World"]
[1,4,2,"Pelican"]
[1,4,3,"914 Club"]
[1,4,4,"Club NARP"]
[1,4,5,"Roadglue"]
[1,5,0,"Design Awards"]
[1,5,1,"Make/Purchase Awards"]
[1,6,0,"Purchase stationary"]
[]
[2,0,0,"Event Registration"]
[2,1,0,"Arrange registration service"]
[2,2,0,"ID $ Collection Method"]
[2,2,1,"Collect Money"]
[2,2,2,"Draft \"Welcome Letters\""]
[2,2,3,"Purchase stamps"]
[2,2,4,"Send \"Welcome Letters\""]
[]
[3,0,0,"Check-In Event",{"$nulls":6},"Thursday"]
[3,1,0,"Coordinate Location"]
[3,2,0,"Source Table & Chairs"]
[3,3,0,"Prepare Goodie Bags"]
[3,3,1,"Buy bags"]
[3,3,2,"Buy name tags"]
[3,3,3,"Personalize name tags"]
[3,3,4,"Collect ad material/freebies"]
[3,3,5,"Prep bags"]
[3,4,0,"Welcome Banner"]
[3,4,1,"Design Banner"]
[3,4,2,"Hang Banner"]
[3,5,0,"Schedule Reg. Times"]
[3,6,0,"Management Plan for Check-In"]
[3,6,1,"Recruit welcome helpers"]
[3,6,2,"Staff the desk"]
[3,6,3,"Sign in Attendees"]
[3,6,4,"Sign PCA Waivers"]
[3,7,0,"Arrange Pizza Dinner"]
[3,7,1,"Budget "]
[3,7,2,"Arrange Hospitality Suite"]
[3,7,3,"Cleanup"]
[3,7,4,"Transition to next event"]
[]
[4,0,0,"Scenic Tour",{"$nulls":6},"Friday"]
[4,1,0,"Schedule Event"]
[4,2,0,"ID Route"]
[4,2,1,"Rehearse Route"]
[4,3,0,"Vehicle Recovery Plan"]
[4,4,0,"Lunch Meal"]
[4,4,1,"ID Restaurant"]
[4,4,2,"ID Cost Estimate"]
[4,5,0,"Acquire radio equipment"]
[4,6,0,"Conduct Run"]
[4,6,1,"Maps for stragglers"]
[4,6,2,"ID lead & trail vehicles"]
[4,6,3,"Start run"]
[4,6,4,"End run"]
[4,7,0,"Transition to next event"]
[]
[5,0,0,"Hare & Hound",{"$nulls":6},"Friday"]
[5,1,0,"Schedule Event"]
[5,2,0,"ID Route"]
[5,2,1,"Rehearse Route"]
[5,3,0,"Vehicle Recovery Plan"]
[5,4,0,"\"Midnight snack\" upon return?"]
[5,4,1,"ID Restaurant"]
[5,4,2,"ID Cost Estimate"]
[5,5,0,"Acquire radio equipment"]
[5,6,0,"Conduct Run"]
[5,6,1,"Maps for stragglers"]
[5,6,2,"ID lead & trail vehicles"]
[5,6,3,"Start run"]
[5,6,4,"End run"]
[5,7,0,"Transition to next event"]
[]
[6,0,0,"Morning Tour",{"$nulls":6},"Saturday"]
[6,1,0,"Schedule Event"]
[6,1,1,"Designate \"gas up\" time before run"]
[6,2,0,"ID Route"]
[6,2,1,"Rehearse Route"]
[6,3,0,"Vehicle Recovery Plan"]
[6,4,0,"Lunch Meal"]
[6,4,1,"ID Restaurant"]
[6,4,2,"ID Cost Estimate"]
[6,5,0,"Acquire radio equipment"]
[6,6,0,"Conduct Run"]
[6,6,1,"Maps for stragglers"]
[6,6,2,"ID lead & trail vehicles"]
[6,6,3,"Start run"]
[6,6,4,"End run"]
[6,7,0,"Transition to next event"]
[]
[7,0,0,"Car Show",{"$nulls":6},"Saturday"]
[7,1,0,"Schedule Event"]
[7,2,0,"Define Parking Areas"]
[7,2,1,"Signs/stakes/tape for parking"]
[7,2,2,"Mark areas by class"]
[7,3,0,"Move cars to areas"]
[7,4,0,"Voting"]
[7,4,1,"Print ballots"]
[7,4,2,"Issue ballots"]
[7,4,3,"Conduct Voting"]
[7,4,4,"Collect ballots"]
[7,4,5,"Tabulate votes"]
[7,5,0,"Write rules"]
[7,5,1,"Review/Change/Validate Rules"]
[7,5,2,"Publish rules on website"]
[7,6,0,"Judge Best of Show Class"]
[7,6,1,"ID Judges"]
[7,6,2,"Invite Judges"]
[7,6,3,"\"thank you\" token to judges"]
[7,7,0,"Transition to next event"]
[]
[8,0,0,"Tech Quiz"]
[8,1,0,"ID Location"]
[8,2,0,"Write Quiz"]
[8,3,0,"Print Quiz & Answer Sheets"]
[8,3,1,"Pay for paper"]
[8,4,0,"Issue Pencils"]
[8,4,1,"Pay for pencils"]
[8,5,0,"Grade Quiz"]
[8,6,0,"ID Winners"]
[8,7,0,"Transition to next event"]
[]
[9,0,0,"Awards Dinner",{"$nulls":6},"Saturday"]
[9,1,0,"Schedule Event"]
[9,2,0,"ID Location"]
[9,3,0,"Food"]
[9,4,0,"ID Menu"]
[9,4,1,"ID Cost Estimate"]
[9,4,2,"Add cost to Registration Fee"]
[9,5,0,"Happy Hour??  (yes/no)",{"$nulls":6},"yes"]
[9,6,0,"Get people to dinner",{"$nulls":6},"Caravan from Hotel"]
[9,7,0,"Door Prizes"]
[9,7,1,"Write Solicitations"]
[9,7,2,"Mail Solicitations"]
[9,7,3,"Transport prizes to dinner"]
[9,7,4,"Plan prize method"]
[9,7,5,"Awards & door prizes"]
[9,8,0,"Keynote speaker"]
[9,9,0,"Acquire Awards"]
[9,9,1,"Keynote speaker \"thank you\"",{"$nulls":6},"Acquire awards."]
[9,9,2,"Judges \"thank you\"",{"$nulls":6},"Acquire awards."]
[9,9,3,"Long Distance",{"$nulls":6},"Acquire awards."]
[9,9,4,"AX Awards",{"$nulls":6},"Acquire awards."]
[9,9,5,"Tech Quiz Awards",{"$nulls":6},"Acquire awards."]
[9,9,6,"Poker Run Awards",{"$nulls":6},"Acquire awards."]
[9,9,7,"Car Show Awards",{"$nulls":6},"Acquire awards."]
[9,9,8,"People's Choice",{"$nulls":6},"Acquire awards."]
[9,9,9,"Best of Show",{"$nulls":6},"Acquire awards."]
[9,10,0,"Lead people home",{"$nulls":6},"maps for stragglers"]
[9,10,1,"Designated Driver Plan"]
[9,11,0,"Farewell/Transition to next event"]
[]
[10,0,0,"Blind Autocross",{"$nulls":6},"Sunday"]
[10,1,0,"Get approval from Hotel"]
[10,2,0,"Plan to clear parking lot"]
[10,3,0,"ID Safeties"]
[10,4,0,"Acquire Awards"]
[10,5,0,"Awards Presentation"]
[10,6,0,"Farewell"]
[]
[]
[]
["?",0,0,"Tech Session"]
["?",1,0,"Get Car to Session"]
["?",2,0,"ID Parts?"]
["?",2,1,"Order any emergency parts"]
["?",2,1,"Have Parts On-Hand"]
["?",3,0,"Schedule Time"]
["?",4,0,"Validate Tools"]
["?",5,0,"Rehearse Class"]
["?",5,1,"Schedule Time"]
["?",5,2,"Execute Rehearsal"]
["?",5,3,"Practice class"]
["?",8,0,"Transition to next event"]
[]
["?",0,0,"Swap Meet"]
["?",1,0,"ID Location"]
["?",2,0,"Get Tables"]
["?",3,0,"Get Coffee & Cups"]
[]
["?",0,0,"Carwash Stuff"]
["?",1,0,"ID Location"]
["?",2,0,"Get Hoses"]
["?",3,0,"Get Buckets"]
["?",4,0,"Block off parking areas"]